RESEARCH PROPOSAL REPORT

DermaGuard: Artifact-Robust and Uncertainty-Calibrated Skin Lesion Classification with Lesion-Guided Explanations and Selective Referral

A research-ready medical imaging project using the public ISIC 2018 and HAM10000 resources

| Item | Details |
| --- | --- |
| Student Name | [Enter student name] |
| Registration Number | [Enter registration number] |
| Programme / Department | [Enter programme and department] |
| Supervisor | [Enter supervisor name] |
| Institution | [Enter institution name] |
| Date | July 2026 |

Prepared for research approval and implementation planning.

# Executive Summary

This proposal presents a complete, research-ready medical imaging project for automated multi-class skin-lesion analysis. The study uses public dermoscopic datasets from the International Skin Imaging Collaboration (ISIC), including 10,015 diagnosis-labelled images from the ISIC 2018 classification task and 2,594 images with expert lesion-boundary annotations from the segmentation task. The project requires no hospital collaboration, new patient recruitment, electronic health records, or manual medical annotation.

The proposed system first segments the lesion using a lightweight U-Net and then performs seven-class diagnosis using EfficientNet-B0. Its publishable focus is not merely higher classification accuracy. The study evaluates whether lesion-guided learning reduces background and artifact dependence, whether predictions remain reliable under hair, ruler, blur and illumination corruption, and whether calibrated uncertainty can safely refer unreliable cases to a clinician instead of forcing a diagnosis.

| Requirement | Status |
| --- | --- |
| Public images | Available through the ISIC Challenge repository |
| Diagnosis labels | Available for 10,015 training images |
| Segmentation masks | Available for 2,594 segmentation images |
| Baseline tasks | ISIC 2018 Tasks 1 and 3 |
| Pretrained models | U-Net and EfficientNet implementations widely available |
| New clinical data collection | Not required |
| Primary challenge | Avoid data leakage, class imbalance and overconfident predictions |
| Research readiness | Ready to begin after dataset download and licence review |

## Recommended Final Title

Artifact-Robust and Uncertainty-Calibrated Skin Lesion Classification with Lesion-Guided Explanations and Selective Referral

## Short Conference Title

DermaGuard: Reliable Skin Lesion Classification under Artifacts and Uncertainty

# 1. Research Domain and Scope

| Category | Selected Scope |
| --- | --- |
| Domain | Artificial Intelligence in Healthcare |
| Subdomain | Medical image analysis and computer-aided dermatology |
| Image type | Dermoscopy |
| Primary task | Seven-class skin lesion classification |
| Supporting task | Lesion-boundary segmentation |
| Trustworthiness focus | Artifact robustness, explainability, calibration and selective referral |
| Dataset | ISIC 2018 / HAM10000 |
| Intended use | Research decision-support prototype; not autonomous clinical diagnosis |

## 1.1 Why this topic is manageable

The images, diagnosis labels and segmentation annotations are already public.

The study uses standard two-dimensional images rather than long clinical time series.

A U-Net and EfficientNet-B0 can be trained on a single modern GPU.

The research can be divided into small, independently testable modules.

The dataset has established benchmark tasks and published baselines.

No protected EHR or hospital approval is required for the public benchmark work, subject to institutional policy and licence compliance.

## 1.2 Why the topic is still research-worthy

Skin-lesion classification is a mature area, so a paper that only fine-tunes another CNN is unlikely to be sufficiently novel. The proposed study instead evaluates reliability. It asks whether the model looks at the lesion, remains stable when artifacts are introduced, produces calibrated confidence and knows when to defer a case. This changes the contribution from a routine classifier to a trustworthy medical-imaging evaluation framework.

# 2. Background and Motivation

Dermoscopic images contain visual patterns that help dermatologists distinguish common pigmented skin lesions. Deep learning can learn these patterns, but high benchmark accuracy does not guarantee safe behaviour. Models may depend on hair, rulers, colour calibration marks, dark corners, acquisition style or surrounding skin. They may also produce high confidence for incorrect predictions.

A practical screening system should satisfy four requirements: it should localise the lesion, base its decision mainly on lesion evidence, remain reasonably robust to common image artifacts, and refer uncertain cases for expert assessment. The proposed study addresses these requirements using existing public data and reproducible stress tests.

# 3. Problem Statement

Existing deep-learning systems for dermoscopic skin-lesion classification often optimise accuracy on clean benchmark images. They do not consistently verify whether predictions are based on the lesion rather than background artifacts, and they may remain overconfident when image quality is poor or the input differs from the training distribution. Separate segmentation, classification, explanation and uncertainty studies exist, but these components are not always evaluated together through a clinically meaningful referral mechanism. Therefore, a lightweight lesion-guided framework is required that classifies common skin lesions, quantifies explanation overlap with the lesion, evaluates robustness under realistic artifacts, calibrates prediction confidence and defers unreliable cases.

# 4. Research Gap

| Gap | Why it matters |
| --- | --- |
| Accuracy-first evaluation | Many studies report accuracy, AUC or F1 without testing performance under realistic image corruption. |
| Weak explanation validation | Grad-CAM images are often displayed qualitatively but are not measured against lesion boundaries. |
| Artifact dependence | Hair, ruler marks and illumination can influence predictions; robustness is not routinely benchmarked. |
| Overconfidence | Softmax scores are commonly treated as confidence even when they are poorly calibrated. |
| Forced prediction | Models generally return a diagnosis for every image rather than referring uncertain cases. |
| Data leakage risk | Repeated views of the same lesion and duplicate images can inflate results if split incorrectly. |
| Class imbalance | The nevus class dominates HAM10000, while dermatofibroma and vascular lesions are rare. |

## 4.1 Final gap statement

Public skin-lesion studies provide strong classification and segmentation baselines, but there remains a practical need for a reproducible framework that jointly measures lesion-centred explanation quality, artifact robustness, probability calibration and selective referral using lesion-aware data splits. The proposed work fills this evaluation gap with a lightweight two-stage model and controlled corruption tests.

# 5. Aim, Objectives and Research Questions

## 5.1 Aim

To develop and evaluate a lesion-guided skin-lesion classification system that remains reliable under common dermoscopic artifacts and refers uncertain cases for expert review.

## 5.2 Objectives

Train a U-Net model for lesion-boundary segmentation using ISIC 2018 Task 1.

Train an EfficientNet-B0 model for seven-class lesion diagnosis using ISIC 2018 Task 3.

Use predicted lesion masks to crop, gate or weight classification features.

Create controlled hair, ruler, blur, brightness and compression stress tests.

Quantitatively evaluate whether Grad-CAM explanations lie inside the lesion region.

Estimate uncertainty through Monte Carlo dropout and calibrate probabilities with temperature scaling.

Implement selective referral and evaluate the accuracy-coverage trade-off.

Release reproducible lesion-level splits, code and experiment configurations.

## 5.3 Research questions

RQ1: Does lesion-guided classification improve balanced accuracy and macro-F1 over full-image classification?

RQ2: Does artifact-aware training reduce performance loss under hair, ruler and illumination corruption?

RQ3: Do lesion-guided models show lower background attribution and higher explanation-mask overlap?

RQ4: Does calibration reduce expected calibration error without reducing discrimination performance?

RQ5: Can uncertainty-based referral improve retained-case accuracy while referring a manageable proportion of cases?

# 6. Dataset and Resource Plan

## 6.1 ISIC 2018 resources

The ISIC 2018 challenge provides separate tasks for lesion segmentation and disease classification. The classification task contains 10,015 diagnosis-labelled dermoscopic images. The segmentation task contains 2,594 images with multiple expert response masks. The project uses the two task sets in a two-stage design: the segmentation model is trained on Task 1, and its predicted masks are applied to Task 3 images before classification.

| Resource | Content | Use in this project |
| --- | --- | --- |
| Task 1 training set | 2,594 dermoscopic images with expert lesion-boundary masks | Train and validate U-Net segmentation |
| Task 3 training set | 10,015 dermoscopic images with seven diagnosis classes | Train and test EfficientNet-B0 classifier |
| Supplemental lesion data | Lesion grouping and diagnosis-confirmation information | Create lesion-aware splits and report label provenance |
| Challenge test/validation resources | Official held-out benchmark resources where accessible | Optional secondary evaluation |

## 6.2 Diagnostic classes

| Code | Diagnosis | Approx. images |
| --- | --- | --- |
| NV | Melanocytic nevi | 6,705 |
| MEL | Melanoma | 1,113 |
| BKL | Benign keratosis-like lesions | 1,099 |
| BCC | Basal cell carcinoma | 514 |
| AKIEC | Actinic keratoses / intraepithelial carcinoma | 327 |
| VASC | Vascular lesions | 142 |
| DF | Dermatofibroma | 115 |

Because the dataset is strongly imbalanced, overall accuracy will not be used as the main metric. Macro-F1, balanced accuracy, per-class sensitivity and class-balanced loss will be prioritised.

## 6.3 Data split strategy

Split by lesion identifier rather than by individual image.

Keep all images of the same lesion in one partition.

Use a fixed training, validation and test split, such as 70:15:15 at lesion level.

Perform five repeated lesion-level runs or five-fold cross-validation where computationally feasible.

Check and remove exact or near-duplicate leakage using published duplicate lists and perceptual hashes.

## 6.4 Licensing and governance

The dataset must be used according to the ISIC licence and attribution requirements. Images must not be re-identified or represented as a clinical service. Institutional review requirements should be confirmed with the supervisor, even though the proposed work uses public deidentified benchmark data.

# 7. Proposed Methodology

Figure 1. Proposed two-stage segmentation, classification, uncertainty and referral pipeline.

## 7.1 Stage A: Image preparation

Resize images to 224 x 224 for classification and 256 x 256 for segmentation.

Apply colour normalisation without removing clinically meaningful colour variation.

Use horizontal/vertical flips, rotation, scale and mild colour augmentation.

Create artifact augmentations for hair, rulers, blur, JPEG compression, darkness and overexposure.

Store an artifact severity label for each synthetic stress-test image.

## 7.2 Stage B: Lesion segmentation

A standard U-Net will be trained using the Task 1 images and masks. The initial loss will combine binary cross-entropy and Dice loss. The segmentation model will output a lesion-probability map. A binary mask will be produced using a validation-selected threshold.

| Component | Recommended setting |
| --- | --- |
| Architecture | U-Net with a ResNet18 or lightweight encoder |
| Input | 256 x 256 RGB image |
| Loss | 0.5 binary cross-entropy + 0.5 Dice loss |
| Metrics | Dice coefficient, Jaccard/IoU, sensitivity and specificity |
| Output use | Lesion crop, soft attention mask and explanation reference |

## 7.3 Stage C: Lesion-guided classification

EfficientNet-B0 will be used because it offers a practical accuracy-computation balance. Three input variants will be compared: the complete image, a bounding-box lesion crop and a soft mask-gated image. The classifier will produce seven class probabilities.

Use ImageNet pretrained weights.

Replace the final layer with a seven-class head.

Apply class-balanced focal loss or weighted cross-entropy.

Use dropout before the classification head.

Select the final model using validation macro-F1, not raw accuracy.

## 7.4 Stage D: Explainability

Grad-CAM will be computed for the predicted class. Instead of only presenting heatmaps, explanation quality will be measured against the predicted or expert lesion mask.

| Explanation metric | Interpretation |
| --- | --- |
| Lesion attribution ratio | Fraction of positive attribution lying inside the lesion mask |
| Background leakage ratio | Fraction of positive attribution outside the lesion |
| Pointing-game accuracy | Whether the maximum attribution point falls inside the lesion |
| Deletion test | Prediction reduction after removing the most attributed pixels |
| Stability | Similarity of explanations under mild image transformations |

## 7.5 Stage E: Uncertainty and calibration

At inference, dropout remains active for multiple forward passes. The mean probability becomes the final prediction and the variation across passes estimates epistemic uncertainty. Temperature scaling is fitted using only the validation set.

Run 20 Monte Carlo dropout passes per image.

Calculate predictive entropy and probability variance.

Report expected calibration error, Brier score and negative log-likelihood.

Compare raw softmax, temperature scaling and Monte Carlo dropout.

## 7.6 Stage F: Selective referral

A case is referred when uncertainty exceeds a threshold, maximum calibrated probability is too low, or the segmentation mask is implausible. Performance will be reported at multiple retained-case coverages.

| Decision | Example rule |
| --- | --- |
| Automatic prediction | Calibrated maximum probability >= threshold and low predictive entropy |
| Expert referral | High entropy, low confidence or abnormal lesion-mask area |
| Research-only output | Predicted class, confidence, mask, heatmap and referral reason |

# 8. Experimental Design

## 8.1 Baseline models

| ID | Baseline |
| --- | --- |
| B1 | Majority-class and class-prior baselines |
| B2 | EfficientNet-B0 trained on full images |
| B3 | EfficientNet-B0 trained on lesion crops |
| B4 | U-Net + crop-based EfficientNet without artifact augmentation |
| B5 | Artifact-aware EfficientNet without uncertainty |
| B6 | Proposed lesion-guided, artifact-aware and calibrated model |

## 8.2 Main experiments

| Experiment | Purpose |
| --- | --- |
| E1 - Clean classification | Evaluate all models on the lesion-level clean test set. |
| E2 - Segmentation | Evaluate U-Net on the Task 1 held-out set. |
| E3 - Artifact robustness | Test 3-5 severity levels of hair, rulers, blur, brightness and compression. |
| E4 - Explanation overlap | Measure lesion attribution and background leakage. |
| E5 - Calibration | Compare softmax, temperature scaling and Monte Carlo dropout. |
| E6 - Selective referral | Plot accuracy, macro-F1 and error against retained-case coverage. |
| E7 - Ablation | Remove segmentation guidance, artifact augmentation, calibration and referral components. |
| E8 - Rare-class analysis | Report class-wise results and confusion among clinically similar classes. |

## 8.3 Artifact stress-test protocol

| Artifact | Simulation | Evaluation |
| --- | --- | --- |
| Hair | Overlay curved dark and light strands of increasing density | Performance drop versus clean images |
| Ruler marks | Overlay thin high-contrast lines and tick marks | Check whether saliency shifts to rulers |
| Blur | Gaussian blur at increasing strength | Calibration under reduced detail |
| Illumination | Brightness, contrast and colour-temperature shifts | Robustness to acquisition variation |
| Compression | JPEG quality reduction | Robustness to low-quality image transfer |

# 9. Evaluation Metrics and Statistical Analysis

| Task | Primary metrics |
| --- | --- |
| Segmentation | Dice coefficient, IoU/Jaccard, sensitivity, specificity |
| Classification | Balanced accuracy, macro-F1, one-vs-rest AUROC, per-class sensitivity and specificity |
| Calibration | Expected calibration error, Brier score, negative log-likelihood |
| Referral | Risk-coverage curve, retained-case accuracy, referral rate |
| Explanation | Lesion attribution ratio, background leakage, pointing-game accuracy |
| Robustness | Relative performance degradation from clean to corrupted conditions |

## 9.1 Statistical reporting

Report mean and standard deviation across repeated lesion-level splits.

Use paired bootstrap confidence intervals for differences in macro-F1 or AUROC.

Apply a paired non-parametric test across repeated runs when distributional assumptions are uncertain.

Correct for multiple comparisons when testing several artifact conditions.

Include confidence intervals, not only p-values.

# 10. Expected Novel Contributions

The proposed paper will not claim that U-Net, EfficientNet, Grad-CAM or Monte Carlo dropout are new. Its novelty is the integrated, reproducible evaluation design.

A lesion-aware data-splitting and duplicate-control protocol for ISIC 2018 experiments.

A simple lesion-guided classifier evaluated against full-image and crop-based baselines.

A controlled dermoscopic artifact stress-test suite with graded corruption severity.

Quantitative lesion-overlap validation of model explanations.

Calibration and selective-referral evaluation under both clean and corrupted images.

An analysis of whether uncertainty increases when explanations move away from the lesion.

Reproducible code, configurations and test splits for follow-up research.

## 10.1 Safe novelty statement for the paper

This study presents a reproducible reliability framework for seven-class dermoscopic lesion analysis that jointly evaluates lesion-guided classification, artifact-induced distribution shift, quantitative explanation alignment, probability calibration and uncertainty-based selective referral.

# 11. Implementation Requirements

| Category | Recommended resources |
| --- | --- |
| Programming | Python 3.11, PyTorch, torchvision, segmentation-models-pytorch |
| Image processing | OpenCV, Pillow and Albumentations |
| Analysis | NumPy, pandas, scikit-learn, SciPy |
| Explainability | Captum or custom Grad-CAM implementation |
| Experiment tracking | TensorBoard, MLflow or Weights & Biases |
| GPU | One NVIDIA GPU with approximately 8-12 GB VRAM |
| Storage | Approximately 20-30 GB including images, masks, checkpoints and generated corruptions |
| Version control | Git repository with fixed seeds and environment file |

# 12. Work Plan

| Week | Activity |
| --- | --- |
| 1-2 | Download data, verify licences, build lesion-level index and duplicate checks |
| 3-4 | Implement preprocessing, augmentations and fixed splits |
| 5-7 | Train and validate U-Net segmentation model |
| 8-10 | Train full-image and crop-based EfficientNet baselines |
| 11-12 | Implement lesion-guided classification and class balancing |
| 13-14 | Create artifact stress tests and robustness analysis |
| 15-16 | Implement calibration, Monte Carlo dropout and referral |
| 17 | Run ablations, repeated experiments and statistical analysis |
| 18 | Prepare figures, tables and explanation examples |
| 19 | Write conference manuscript |
| 20 | Internal review, reproducibility check and submission preparation |

# 13. Risks and Mitigation

| Risk | Mitigation |
| --- | --- |
| Class imbalance causes majority-class bias | Use class-balanced loss, macro metrics and controlled sampling. |
| Segmentation masks and classification images are separate task sets | Train the segmenter separately, then infer masks on all classification images. |
| Duplicate or lesion leakage inflates results | Use lesion identifiers, published duplicate analysis and perceptual hashing. |
| Synthetic artifacts appear unrealistic | Use multiple shapes/severities and manually inspect generated samples. |
| Uncertainty does not correlate with errors | Compare several scores and use validation-based calibration. |
| Grad-CAM remains unstable | Report transformation stability and deletion tests, not screenshots alone. |
| Small rare classes give wide uncertainty | Report confidence intervals and avoid overstating subgroup conclusions. |
| Clinical claims exceed evidence | Describe the system as research decision support and require expert referral. |

# 14. Ethical and Clinical Considerations

The model is not a replacement for dermatologist diagnosis.

The output should be described as a research screening or decision-support result.

Malignant-class sensitivity and referral behaviour should be prioritised over overall accuracy.

Dataset demographic limitations and underrepresentation of darker skin tones must be discussed.

Model confidence is not equivalent to clinical certainty.

Any future prospective clinical use would require ethics approval, external validation and regulatory review.

# 15. Literature Review Summary

| Paper / resource | Main contribution | Relevance and remaining gap |
| --- | --- | --- |
| Tschandl et al., 2018 - HAM10000 | Released 10,015 multi-source dermoscopic images with seven diagnostic categories. | Provides the classification dataset; class imbalance and domain diversity remain challenges. |
| Codella et al., 2019 - ISIC 2018 challenge | Defined segmentation, attribute and diagnosis benchmark tasks. | Provides official tasks and baselines but not a unified reliability evaluation. |
| Cassidy et al., 2022 - ISIC analysis | Analysed duplicates, dataset usage and benchmark recommendations. | Supports lesion-aware splits and duplicate control. |
| Zhang et al., 2019 - attention residual learning | Introduced attention-based lesion classification. | Attention improves localisation, but attention is not automatically a validated explanation. |
| DermoExpert, 2022 | Combined lesion segmentation, transfer learning and augmentation. | Supports two-stage modelling; calibration and referral need deeper analysis. |
| ChimeraNet, 2022 | Detected hair and ruler artifacts in dermoscopic images. | Shows artifacts are a real technical issue. |
| Lee et al., 2021 - uncertainty modelling | Jointly modelled dermatological classification and confidence. | Supports uncertainty estimation; the proposed study adds artifact stress testing and referral. |
| Gal and Ghahramani, 2016 | Interpreted dropout as approximate Bayesian inference. | Provides the basis for Monte Carlo dropout. |
| Guo et al., 2017 | Evaluated calibration of modern neural networks and temperature scaling. | Provides the calibration method. |
| Selvaraju et al., 2017 - Grad-CAM | Introduced gradient-based visual explanations. | Provides heatmaps; the proposed study quantitatively checks lesion overlap. |

# 16. Publication Strategy

## 16.1 Primary realistic target

IEEE International Symposium on Computer-Based Medical Systems (CBMS), next suitable edition. CBMS focuses on computer-based medical systems, medical informatics and biomedical informatics. The 2027 call and dates should be checked when officially announced.

## 16.2 Stronger imaging target

IEEE International Symposium on Biomedical Imaging (ISBI) 2027, scheduled for 25-28 May 2027 in Lausanne, Switzerland. ISBI is highly relevant because the work combines biomedical-image segmentation, classification, explainability and reliability. Its submission deadline was still listed as forthcoming when this report was prepared.

## 16.3 Journal-extension options

Biomedical Signal Processing and Control

Computers in Biology and Medicine

Computer Methods and Programs in Biomedicine

Diagnostics

Scientific Reports, provided the experiments and external validation are strong

## 16.4 Minimum paper package

Complete lesion-aware split and duplicate-control description

Clean and corrupted test results

Segmentation and classification baselines

Calibration and selective-referral curves

Quantitative explanation-overlap evaluation

Ablation study and confidence intervals

Public code and reproducibility files

# 17. Readiness Assessment

| Publication requirement | Current status |
| --- | --- |
| Topic and scope | Ready |
| Public image dataset | Available |
| Diagnosis labels | Available |
| Lesion masks | Available |
| Baseline architectures | Available |
| Research gap | Defined |
| Methodology | Defined |
| Experiments and metrics | Defined |
| New clinical annotation | Not required |
| Implementation and results | Still to be completed |
| Publication guarantee | Not possible; acceptance depends on experimental quality and review |

## 17.1 Final recommendation

Proceed with DermaGuard as the third research-ready medical topic. It is easier than multimodal EHR research because it uses standard images and public labels, and it is more publication-oriented than a routine classifier because it evaluates artifacts, explanation alignment, calibration and safe referral.

# 18. Supervisor Approval Checklist

☐ Approve the final title and two-stage design.

☐ Approve ISIC 2018 / HAM10000 as the primary dataset.

☐ Approve lesion-level splitting and duplicate-control protocol.

☐ Approve U-Net and EfficientNet-B0 as initial baseline architectures.

☐ Approve the artifact stress-test and uncertainty-based referral as the main research contribution.

☐ Approve CBMS as the practical conference target and ISBI 2027 as the stronger target.

☐ Identify a dermatologist or medical-imaging expert for optional qualitative review of explanations.

# References

[1] N. C. F. Codella et al., “Skin Lesion Analysis Toward Melanoma Detection 2018: A Challenge Hosted by the International Skin Imaging Collaboration (ISIC),” arXiv:1902.03368, 2019.

[2] P. Tschandl, C. Rosendahl, and H. Kittler, “The HAM10000 dataset, a large collection of multi-source dermatoscopic images of common pigmented skin lesions,” Scientific Data, vol. 5, Art. no. 180161, 2018, doi:10.1038/sdata.2018.161.

[3] B. Cassidy et al., “Analysis of the ISIC image datasets: Usage, benchmarks and recommendations,” Medical Image Analysis, vol. 75, Art. no. 102305, 2022.

[4] O. Ronneberger, P. Fischer, and T. Brox, “U-Net: Convolutional Networks for Biomedical Image Segmentation,” in MICCAI, 2015, pp. 234-241.

[5] M. Tan and Q. V. Le, “EfficientNet: Rethinking Model Scaling for Convolutional Neural Networks,” in ICML, 2019.

[6] R. R. Selvaraju et al., “Grad-CAM: Visual Explanations from Deep Networks via Gradient-Based Localization,” in ICCV, 2017.

[7] Y. Gal and Z. Ghahramani, “Dropout as a Bayesian Approximation: Representing Model Uncertainty in Deep Learning,” in ICML, 2016.

[8] C. Guo, G. Pleiss, Y. Sun, and K. Q. Weinberger, “On Calibration of Modern Neural Networks,” in ICML, 2017.

[9] Y. Geifman and R. El-Yaniv, “SelectiveNet: A Deep Neural Network with an Integrated Reject Option,” in ICML, 2019.

[10] J. Zhang, Y. Xie, Y. Xia, and C. Shen, “Attention Residual Learning for Skin Lesion Classification,” IEEE Transactions on Medical Imaging, vol. 38, no. 9, pp. 2092-2103, 2019.

[11] K. Manzoor et al., “Dual-stage segmentation and classification framework for skin lesion analysis,” 2025.

[12] G.-H. Lee, H.-B. Ko, and S.-W. Lee, “Joint Dermatological Lesion Classification and Confidence Modeling with Uncertainty Estimation,” arXiv:2107.08770, 2021.

[13] International Skin Imaging Collaboration, “ISIC Challenge Datasets and 2018 Challenge,” challenge.isic-archive.com, accessed July 2026.

[14] IEEE Computer-Based Medical Systems, “CBMS official conference series,” cbms-conference.org, accessed July 2026.

[15] IEEE Signal Processing Society, “2027 IEEE International Symposium on Biomedical Imaging,” 25-28 May 2027, Lausanne, Switzerland, accessed July 2026.

# Appendix A. Proposed Output Example

| Output field | Example |
| --- | --- |
| Predicted class | Melanoma |
| Calibrated probability | 0.72 |
| Predictive entropy | Moderate |
| Lesion attribution ratio | 0.84 |
| Artifact warning | Hair density: high |
| Decision | Refer to dermatologist |
| Referral reason | Prediction uncertainty exceeds the validated threshold |

Important: the values above are only a display example. The final thresholds must be selected from validation experiments and must not be interpreted as a clinical recommendation.